Halebank Church of England Primary School

School Improvement Plan 2023-2025

‘Let your light shine.’

Matthew 5.16

Halebank Church of England Primary School

Heathview Road

Halebank

Widnes

Cheshire

WA8 8UZ

Tel: (0151) 425 5798

www.halebank.halton.sch.uk

School Vision and Aims

At the heart of Halebank Church of England Primary School is a caring Christian family with one core purpose:

‘Let your light shine.’ Matthew 5.16

We are committed to educating ‘the whole person’ through the four basic elements of wisdom, hope, community and dignity.

As a school, we aspire to:

- Enable learners to grow in the wisdom, creativity, knowledge and skills which provide the foundations for success in life;

- Offer a broad and rich curriculum which stimulates, inspires and builds confidence;

- Provide the hope, encouragement and courage to admit and learn from mistakes, overcome difficulties, and forgive and reconcile;

- Create a climate for learning that is rich in opportunities and high in aspirations;

- Work together to build relationships within and beyond the community, valuing and respecting the contributions of others;

- Contribute positively to the school and wider community through experiences, opportunities and celebrations which promote lifelong learning;

- Teach the value of uniqueness, self-worth and inherent individuality;

- Promote equality and an understanding, acceptance and celebration of diversity.

Principles

The agreed and shared principles for writing the Strategic School Improvement Plan at our school are:

- Success criteria are agreed for all key areas and the improvement plan is delivered through the year;

- The SIP is reviewed by the SLT, staff and governors termly;

- Evaluation of the school’s performance is made against the success criteria and the SIP updated;

- Progress and actions are monitored by the SLT, subject leaders and governors;

- Monitoring activities inform both the school’s ongoing self-evaluation and the identification of emerging priorities for the next academic year.

Contextual Information

| School characteristics |  |
| --- | --- |
| - Christian values and a strong sense of community are at the heart of this small school. Pupils and staff work together as a ‘family’ to achieve their best. - The school benefits from a new building and extensive grounds. - A higher-than-average number of pupils are entitled to free school meals. The number of children from minority ethnic groups has decreased year on year for the last three years and is significantly lower than the national average. - Whilst there are no children currently with EHC plans, there are a slightly higher number of children on SEN support plans than previously and is the case nationally. There have historically been a significant number of pupils new to EYFS, with unidentified needs who have started school. - This smaller than average school has four classes, although the number on roll is increasing slightly each year. - A number of the children receive pre-school education at the privately run nursery sited on the school’s grounds. The pre-school takes children from 2 years old and they aim to be flexible to suit parents’ needs. Children start school full time at the start of the school year prior to their fifth birthday. - Children typically enter the Reception Class below age-related expectations (3-4 years) in most areas, although this can vary slightly from year to year. This is reflected in the baseline assessments, which are carefully carried out within the first few weeks of the academic year. |  |
| Last Inspection Report |  |
| Date: 18th and 19th October 2022 | Overall school effectiveness judgement: Requires Improvement Quality of Education: Requires Improvement Behaviour & Attitudes: Good Personal Development: Good Leadership & Management: Requires Improvement Early Years Provision: Requires Improvement Previous Inspection Grade: Good |
| Ofsted Areas for Improvement: |  |
| ◼ In some subjects, leaders have not clarified all of the specific knowledge that pupils, including children in the early years, must learn. This means that teachers are not as clear as they should be about how to design learning that builds on what pupils already know. Leaders should make sure that they refine their curriculum thinking in these subjects, including in the early years. They should support teachers in designing learning activities that enable pupils to deepen their knowledge and understanding of these subjects over time. ◼ Pupils with SEND have not had their needs met well enough and so they have gaps in their learning. Leaders must make sure that all staff receive the training and support they need so that they can provide pupils with SEND with the help and support they need to achieve well. ◼ Pupils, including children in the early years, who are finding it hard to learn to read are not getting all the support that they need. They are not getting enough practise to learn to read. This means that some pupils are not learning to read as effectively and fluently as they should. Leaders must ensure that staff provide the specific support and practise that these pupils require to be able to read well. ◼ Over time, governors have not held leaders to account for the quality of education that pupils receive. As a result, pupils do not experience a sufficiently well-planned curriculum that enables them to achieve well. Governors should ensure that they ask questions that hold leaders more fully to account for the quality of education that the school provides to pupils. |  |

| Key Priorities for 2023-2025 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Priority 1 Quality of Education | Priority 2 Quality of Education: Reading (including in Early Years) | Priority 3 Inclusion & SEND | Priority 4 Leadership & Management | Priority 5 Church Distinctiveness / SIAMS |
| 1.a. Leaders ensure that all subject leaders provide clarification all of the specific knowledge that pupils, including children in the early years, must learn. 1.b. Teachers are clear about how to design learning that builds on what pupils already know. 1.c. Leaders ensure that subject leaders refine their subject curriculum thinking, including in the early years. 1.d. Leaders support teachers in designing learning activities that enable pupils to deepen their knowledge and understanding of these subjects over time. | 2.a. Pupils (including children in the early years) who are finding it hard to learn to read get all the support that they need. 2. b. All pupils get enough practise to learn to read and therefore read as effectively and fluently as they should. 2. c. Leaders ensure that staff provide the specific support and practise that all pupils require to be able to read well. | 3.a. Pupils with SEND have their needs met well and do not have gaps in their learning. 3. b. Leaders make sure that all staff receive the training and support they need so that they can provide pupils with SEND with the help and support they need to achieve well. | 4.a. Governors hold leaders to account for the quality of education that pupils receive. 4. b. As a result, pupils experience a sufficiently well-planned curriculum that enables them to achieve well. 4. c. Governors ensure that they ask questions that hold leaders more fully to account for the quality of education that the school provides to pupils. | Staff and Governors will develop a whole school community SMSC policy that reflects life in the school. Staff and Governors will evaluate provision for managing and teaching behaviour and attitudes, personal development, SMSC including how these areas are threaded through the whole curriculum. Leaders and Governors will complete the SIAMs SEF. |

Halebank CE Primary SCHOOL DEVELOPMENT PRIORITIES 2023-2025

| Priority1: Quality of Education | Resources Required £ | Objective 1. £ Cornerstones Maestro bought for three years | Objective 1. £ Get set 4 PE bought for 2 years | Objective 1. £ Language Angels annual subscription |  | Objective 1. £ | Review (RAG rated) |  | Delayed |  | On track |  | Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | 1.a |  |  |  | x |  |  |
|  |  |  |  |  |  |  | 1.b |  |  |  | x |  |  |
|  | Person responsible | CW | LP | LE |  |  | 1.c |  |  |  | x |  |  |
|  |  |  |  |  |  |  | 1.d |  |  |  | x |  |  |
| Objectives; |  | Success Criteria |  |  | Actions/Evidence |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Spring 2023 |  | Summer 2023 | Autumn 2023 |  | Spring 2024 |  | Summer 2024 |  |
| 1.a. Leaders ensure that all subject leaders provide clarification all of the specific knowledge that pupils, including children in the early years, must learn. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subject curriculum planning includes the subject knowledge that ALL pupils (including EYFS) must learn. |  | Planning in every subject (including EYFS) includes all the National Curriculum knowledge objectives and additional objectives where possible. Planning reflects ‘disciplinary knowledge’ (identified in the ‘Purpose of Study’ and ‘Aims’ sections of each subject in the National Curriculum) |  |  | Research alternative schemes of work. Analyse suitability and cost effectiveness of schemes of work Spring 1 2023 |  | Cornerstones Maestro (CM) training and exploration in readiness to teach. Implementation of CM Music Lead and Music Teacher begin developing a bespoke music scheme of work for school | Full implementation of CM scheme of work for DT, Art, Science, Geography, History, EYFS Review PE scheme of work |  | Purchase Get Set for PE |  | Review alternative schemes of work for French. Trialling selected scheme in KS2. Music Lead and Music Teacher evaluate progress so far |  |
| - Our (full) curriculum is coherently planned and is sequenced to develop the knowledge (and skills) our pupils will require for their future learning and employment |  | Planning in every subject is sequenced so that the knowledge (and skills) to be taught are coherently laid out and are clear for teaching staff to understand and use. |  |  | Research alternative schemes of work. Analyse suitability and cost effectiveness of schemes of work Spring 1 2023 |  | Cornerstones Maestro (CM) training and exploration in readiness to teach. Implementation of CM Music Lead and Music Teacher begin developing a bespoke music scheme of work for school | Full implementation of CM scheme of work for DT, Art, Science, Geography, History, EYFS Review PE scheme of work |  | Purchase Get Set for PE |  | Review alternative schemes of work for French. Trialling selected scheme in KS2. Music Lead and Music Teacher evaluate progress so far |  |
| Subject curriculum planning is mapped out in a Progression model so that learning of subject knowledge is sequential and builds upon prior curriculum knowledge. |  | Planning in every subject is mapped out so that the subject knowledge in each year groups builds on prior knowledge and shows progression over time (i.e. week by week, half term by half term, term by term etc). Planning is designed so that children are not expected to have subject knowledge, skills and understanding by themselves without sufficient prior knowledge |  |  | Research alternative schemes of work. Analyse suitability and cost effectiveness of schemes of work Spring 1 2023 |  | Cornerstones Maestro (CM) training and exploration in readiness to teach. Implementation of CM Music Lead and Music Teacher begin developing a bespoke music scheme of work for school | Full implementation of CM scheme of work for DT, Art, Science, Geography, History, EYFS Review PE scheme of work |  | Purchase Get Set for PE |  | Review alternative schemes of work for French. Trialling selected scheme in KS2. Music Lead and Music Teacher evaluate progress so far |  |
| 1.b. Teachers are clear about how to design learning that builds on what pupils already know. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| For each subject the curriculum is carefully designed, i.e. new knowledge is broken down into meaningful components and introduced sequentially so it can support all children to learn concepts and knowledge (this includes those with special educational needs and/or disabilities -SEND). |  | Planning in every subject has been considered and set down so that the required knowledge is broken down into sequential ‘bite size’ components - and is inclusive - which will enable all children to learn – including those with SEND. |  |  | Research alternative schemes of work. Analyse suitability and cost effectiveness of schemes of work Spring 1 2023 |  | Cornerstones Maestro (CM) training and exploration in readiness to teach. Implementation of CM Music Lead and Music Teacher begin developing a bespoke music scheme of work for school | Full implementation of CM scheme of work for DT, Art, Science, Geography, History, EYFS Review PE scheme of work |  | Purchase Get Set for PE |  | Review alternative schemes of work for French. Trialling selected scheme in KS2. Music Lead and Music Teacher evaluate progress so far |  |
| 1.c. Leaders ensure that subject leaders refine their subject curriculum thinking, including in the early years. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Teachers have the expertise and subject knowledge to teach and lead all subjects so that pupils develop detailed knowledge (and skills) across the curriculum and, as a result, achieve well |  | An audit of teachers’ CPD needs forms the basis of identifying their needs and supports leaders in creating a strategy/plan to meet those needs. |  |  | SLT training with Cornerstones Maestro |  | Teaching Staff training with Cornerstones Maestro |  |  |  |  |  |  |
|  |  | Subject Leaders complete evaluations of their CPD and evidence the impact of it. |  |  |  |  |  | English and Maths training sessions evaluated for Subject Leads |  |  |  |  |  |
|  |  | Subject leaders engage regularly with other local schools and/or schools in other areas to network and develop their subject leadership skills |  |  |  |  | Three Saints MAT English and Maths support including training | Three Saints MAT English and Maths support including training |  | PEIA projects started for English and Maths inc cluster group moderation |  |  |  |
|  |  | All subject leaders have joined their professional Subject Association and shared subject specific information with other teachers https://www.subjectassociations.org.uk/wp-content/uploads/2020/04/CfSA-Subject-Assocation-Directory-2020.pdf |  |  | PHSE Association Geography Association History Association |  |  | CPD linked to PEIA projects in reading, writing and maths |  | Teachers developing Padlet as a place to store all evidence of monitoring, documents and CPD |  |  |  |
| 1.d. Leaders support teachers in designing learning activities that enable pupils to deepen their knowledge and understanding of these subjects over time. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Leaders adopt or construct a curriculum that is ambitious and designed to give all pupils, particularly disadvantaged pupils and pupils with SEND, the knowledge and cultural capital they need to succeed in life. |  | Planning in every subject includes references to knowledge and cultural capital which is relevant and age appropriate and will support ALL children’s learning and development (including those with SEND). Planning will include social, personal, cultural, spiritual and moral references. Planning in every subject is enhanced by enquiry experiences (e.g. teachers talking to children about subject related content, extra-curricular activities or visits). |  |  | See subject leader files and website for full range of enrichment activities used to embed our curriculum and provide the cultural capital our pupils would otherwise miss out on. |  | Music Lead and Music Teacher begin developing a bespoke music scheme of work for school | Full implementation of CM scheme of work for DT, Art, Science, Geography, History, EYFS |  |  |  | Music Lead and Music Teacher evaluate progress so far |  |

Sources of Evidence

| School Improvement Plan | Performance Management | Governor Visit Record | Headteacher’s Report to Governors |
| --- | --- | --- | --- |
| School Self Evaluation Planner | Observation of Teaching and Learning | Planning and Work Scrutiny | Surveys (parents, pupils & staff) Audits of CPD needs – staff |
| Collaboration with other schools and across LA Boundaries | CPD Strategy/Plan | CPD evaluation records | In house and external Moderation |

| Priority 2: Q of E Reading (including in Early Years) | Resources Required £ | Objective 2 £ All training this year has been free of charge | Resources have been updated through grants, donations and school budget. |  |  | Review (RAG rated) |  | Delayed |  | On track |  | Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2.a |  |  |  | x |  |  |
|  |  |  |  |  |  | 2.b |  |  |  | x |  |  |
|  | Person responsible | JB |  |  |  | 2.c |  |  |  | x |  |  |
|  |  |  |  |  |  |  |  |  |  | x |  |  |
| Objectives; | Success Criteria |  |  | Actions/Evidence |  |  |  |  |  |  |  |  |
|  |  |  |  | Spring 2023 |  | Summer 2023 | Autumn 2023 |  | Spring 2024 |  | Summer 2024 |  |
| 2.a. Pupils (including children in the early years) who are finding it hard to learn to read get all the support that they need. |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify which children (including early years) find it hard to read | There is clear identification (using robust assessment data in addition to teacher assessment and AfL) of children who need support for reading. There is a strategic plan in place that identifies who is responsible for the teaching and learning of reading, with ‘What’ and ‘When’ children will receive support and ‘How’ the impact of teaching will be measured. CPD needs of teachers will be identified and a clear plan in place to ensure that they receive appropriate CPD (which they then evaluate and share the impact of their training and development). |  |  | Bottom 20% + pupil lists reviewed |  | Target readers timetabled and interventions taking place. In all classes End of year assessments carried out | Baseline NFER tests carried out |  | TA |  | NFER |  |
| Identify what support and practise children are currently receiving to help them learn to read |  |  |  | Provision reviewed |  | Reading volunteers requested from various sources Rapid reading and phonics resources in place Bug Club resources supplemented New Salford reading assessment materials purchased for target children – inc comprehension assessment. | IDL purchased and introduced for KS2. Support from English Hub started WELLCOM – whole school screening, identification of need, interventions and rescreening (tracker available) |  | Rescreening |  | Rescreening SL creating reading plan for school based on training and support this year – to start in September 2024. Training session Sept 2nd |  |
| Identify any CPD needs of teachers and teaching assistants |  |  |  | Agreement to join the Halton PEIA project for English Shine reading training and roll out. Support from Three Saints Academy Trust |  | Reading training supported by Three Saints Academy | Reading training supported by Three Saints Academy Reading for pleasure training (SL) |  | Fluency training – Childer Thornton English Hub (subject lead and TA) |  |  |  |
| 2. b. All pupils get enough practise to learn to read and therefore read as effectively and fluently as they should. |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure that the children who find it hard to read are those who receive appropriate levels of support and practise to be able to read | There is a strategic plan in place that identifies who is responsible for the teaching and learning of reading, with ‘What’ and ‘When’ children will receive support and ‘How’ the impact of teaching will be measured. |  |  | Bug Club Phonics and Pathways to Read to continue |  | SL reading training begins |  |  |  |  | SL creating reading plan for school based on training and support this year – to start in September 2024. Training session Sept 2nd |  |
| Ensure teaching of early-reading, phonics and reading is prioritised so that it develops every child’s reading fluency, confidence and enjoyment in reading and allows children to access our full curriculum offer | There is a strategic plan in place that identifies who is responsible for the teaching and learning of reading, with ‘What’ and ‘When’ children will receive support and ‘How’ the impact of teaching will be measured. |  |  | Developing current schemes and practices with support from Childre Thornton and Three Saints |  |  |  |  |  |  | SL creating reading plan for school based on training and support this year – to start in September 2024. Training session Sept 2nd |  |
| 2. c. Leaders ensure that staff provide the specific support and practise that all pupils require to be able to read well. |  |  |  |  |  |  |  |  |  |  |  |  |
| Ensure that teachers and teaching assistants have the required CPD necessary for them to teach all children to read well | CPD needs of teachers will be identified and a clear plan in place to ensure that they receive appropriate CPD (which they then evaluate and share the impact of their training and development). |  |  | Developing current schemes and practices with support from Childre Thornton and Three Saints |  |  |  |  |  |  | SL creating reading plan for school based on training and support this year – to start in September 2024. Training session Sept 2nd |  |
| Ensure robust monitoring of all teaching of reading and children’s outcomes in reading takes place. | A robust School Self-Evaluation Schedule includes monitoring of all teaching of reading and children’s outcomes in reading & phonics. |  |  |  |  | NFER tests SSRT Star reader Phonics assessments To continue INSIGHT used to record data | NFER tests SSRT Star reader Phonics assessments To continue INSIGHT used to record data |  | NFER tests SSRT Star reader Phonics assessments To continue INSIGHT used to record data |  | SL creating reading plan for school based on training and support this year – to start in September 2024. Training session Sept 2nd |  |

Sources of Evidence

| School Improvement Plan | Performance Management | Governor Visit Record | Headteacher’s Report to Governors |
| --- | --- | --- | --- |
| School Self Evaluation Planner | Observation of Teaching and Learning | Planning and Work Scrutiny | Surveys (parents, pupils & staff) Audits of CPD needs – staff |
| Collaboration with other schools and across LA Boundaries | CPD Strategy/Plan | CPD evaluation records | In house and external Moderation |
| English & Reading Polices | Subject Policies | Reading Assessment data and analysis of tracking | Reports to governors, minutes of meetings |

| Priority 3: Inclusion & SEND | Resources Required £ | Objective 3.a £ | Objective 3.b £ | £ |  | £ | Review (RAG rated) |  | Delayed |  | On track |  | Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | 3.a |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 3.b |  |  |  |  |  |  |
|  | Person responsible |  |  |  |  |  |  |  |  |  |  |  |  |
| Objectives; |  | Success Criteria |  |  | Actions/Evidence |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Spring 2023 |  | Summer 2023 | Autumn 2024 |  | Spring 2024 |  | Summer 2024 |  |
| 3.a. Pupils with SEND have their needs met well and do not have gaps in their learning. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Carry out monitoring in all subjects to ensure that the quality of teaching meets the needs of all children with SEN (eg curriculum planning, observations, work scrutiny, assessments, outcomes, pupil voice, monitoring etc) |  | A review of the quality of teaching in every subject to ensure that it meets the needs of all children with SEND will give senior leaders and governors confirmation of how well the children’s needs are being met – and where to target CPD and support more effectively. |  |  | Return of SENDCo from maternity leave. Spring 2 2023 SENDCo has one day a week non-contact time. 2023-2024 ongoing |  | Specialist teacher working with identified pupils. 2023-2024 Monitoring SEND plans | Monitoring SEND plans |  | Monitoring SEND plans |  | Book look |  |
| - Identify the progress children with SEND are making and determine if progress is accelerated so that attainment gaps are closing between pupils with SEN and those without. |  | Robustly monitoring the progress of children with SEND against other pupil groups will ensure that any attainment gaps are not only identified but are also measured and appropriate interventions and assessments are put in place to minimise any such gaps. This will be evidenced in half termly & termly assessment data and tracking. |  |  |  |  |  | New Intervention groups established for WELCOMM, SEAL, Reading, writing and 1:1 follow up sessions for maths. |  |  |  | SENDCo data review and analysis |  |
| Determine whether interventions are effective and are delivering value for money |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. b. Leaders make sure that all staff receive the training and support they need so that they can provide pupils with SEND with the help and support they need to achieve well. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Senior leaders ensure that the cycle of staff CPD plans for equipping all staff to better meet the needs of all children – particularly those with SEND |  | An audit of teachers’ CPD needs forms the basis of identifying their needs and supports leaders in creating a strategy/plan to meet those needs. |  |  | Staff training – ADHD, ASD, Trauma, Attachment, Mental Health, Positive Behaviour, WELCOMM see SENDCo files for training dates |  |  | Staff updates on support plan writing and target setting. Sep 2023/Jan 2024 |  | Staff updates on support plan writing and target setting. Sep 2023/Jan 2024 |  |  |  |
|  |  | Subject Leaders complete evaluations of their CPD and evidence the impact of it. |  |  |  |  |  |  |  |  |  |  |  |

Sources of Evidence

| School Improvement Plan | Performance Management | Governor Visit Record | Headteacher’s Report to Governors |
| --- | --- | --- | --- |
| School Self Evaluation Planner | Observation of Teaching and Learning | Planning and Work Scrutiny | Surveys (parents, pupils & staff) Audits of CPD needs – staff |
| Collaboration with other schools and across LA Boundaries | CPD Strategy/Plan | CPD evaluation records | In house and external Moderation |
| SEND and Inclusion Policies | Subject Policies | SEND Register / records | Data – tracking & analysis |

| Priority 4: Leadership & Management | Resources Required £ | Objective 4.a £ | Objective 4.b £ | Objective 4.c £ |  | £ | Review (RAG rated) |  | Delayed |  | On track |  | Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | 4.a |  |  |  |  |  |  |
|  |  |  |  |  |  |  | 4.b |  |  |  |  |  |  |
|  | Person responsible |  |  |  |  |  | 4.c |  |  |  |  |  |  |
| Objectives; |  | Success Criteria |  |  | Actions/Evidence |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Spring 2023 |  | Summer 2023 | Autumn 2023 |  | Spring 2024 |  | Summer 2024 |  |
| 4.a. Governors hold leaders to account for the quality of education that pupils receive. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Governors have an ambitious and clear vision for providing high quality education to all our children. |  | All governors share in, understand and can articulate the school’s vision for providing high quality education to all children and can talk confidently about it. |  |  | New Governors following a recruitment drive Ongoing Gov training through Entrust and Halton LA |  | New Governors following a recruitment drive Governor training with Hazel Fryman (LA SIP) Summer 2023 |  |  | New Governors following a recruitment drive |  |  |  |
| - Governors can articulate our school’s strong, shared values, policies and practices and offer challenge to leaders to ensure that they are fulfilled. |  | Governors are familiar with the school’s shared values, policies and practices and routinely offer challenge to senior leaders (for example by asking questions, seeking clarification). |  |  | Full stakeholder vision and values day held for existing members |  | Governor website audit |  |  |  |  |  |  |
| - Governors analyse attainment and progress data regularly |  | Governors demonstrate challenge by analysing the assessment and progress data that is shared termly by senior leaders |  |  |  |  | HT Report to Governors Introduction to new Maestro scheme of work | HT Report to Governors |  | HT Report to Governors |  | HT Report to Governors |  |
| - There are designated governor roles and is there a programme of monitoring that is well established to ensure that governors are given accurate information about school progress |  | The designated governors engage in a robust monitoring programme and are an integral part of the school’s self-evaluation cycle. This is supported by senior leaders and evidenced in Headteacher Reports to the Governing Body. |  |  |  |  | New committees established | Governors linked to staff members due to capacity. Governor visits to school to meet with staff, pupils and subject leads – safeguarding, RE/CW and SIAMs, SEND, EYFS, Health and Safety, Maths, History, attendance, MFL, Geography, Science, Art, English and DT. 2023-2024 |  | Gov updates on school website |  | New committees established Link governors for staff/subjects filled Summer 2024 (previously governors were linked to individual staff due to low number of governors |  |
| - Subject leaders regularly report directly to governors and share their work |  | Subject leaders report termly to the headteacher and governors, sharing their work through reports, work scrutiny and pupil voice. |  |  |  |  |  |  |  | Staff subject update reports completed Jan 2024 |  |  |  |
| 4. b. As a result, pupils experience a sufficiently well-planned curriculum that enables them to achieve well. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Governors are confident that senior leaders are developing and improving teachers’ subject, pedagogical and pedagogical subject content knowledge so they enhance the teaching of our curriculum and use assessment appropriately |  | Governors know that the CPD needs of teachers have been identified and a clear plan is in place to ensure that they receive appropriate CPD (which subject leaders have then evaluated and shared the impact of their training and development). |  |  | Plans to make changes to schemes of work were discussed |  | Introduction to new Maestro scheme of work | 2x CS committee meetings a term to review new curriculum developments (AFI 1) Autumn 2023 – Summer 2025 Governor visits to school to meet with staff, pupils and subject leads –RE/CW, SEND, EYFS, Maths, History, MFL, Geography, |  | Maestro updates |  |  |  |
| 4. c. Governors ensure that they ask questions that hold leaders more fully to account for the quality of education that the school provides to pupils. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Governors regularly hold senior leaders to account for the quality of the curriculum |  | Governors routinely offer challenge to senior leaders (for example by asking questions, seeking clarification). |  |  | See minutes from meetings |  |  |  |  |  |  |  |  |

Sources of Evidence

| School Improvement Plan | Performance Management | Governor Visit Record | Headteacher’s Report to Governors |
| --- | --- | --- | --- |
| School Self Evaluation Planner | Observation of Teaching and Learning | Planning and Work Scrutiny | Surveys (parents, pupils & staff) Audits of CPD needs – staff |
| Collaboration with other schools and across LA Boundaries | CPD Strategy/Plan | CPD evaluation records | In house and external Moderation |
| Governing Body Minutes | Committee Meeting Minutes |  |  |

| Priority 5: Church Distinctiveness / SIAMS | Resources Required £ | Objective 5.a £ | Objective 5.b £ |  | Objective 5.c £ | Review (RAG rated) |  | Delayed |  | On track |  | Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 5.a |  |  |  |  |  |  |
|  |  |  |  |  |  | 5.b |  |  |  |  |  |  |
|  | Person responsible |  |  |  |  | 5.c |  |  |  |  |  |  |
| Objectives; | Success Criteria |  |  | Actions/Evidence |  |  |  |  |  |  |  |  |
|  |  |  |  | Spring 2023 |  | Summer 2023 | Autumn 2024 |  | Spring 2024 |  | Summer 2024 |  |

Sources of Evidence

| School Improvement Plan | Performance Management | Governor Visit Record | Headteacher’s Report to Governors |
| --- | --- | --- | --- |
| School Self Evaluation Planner | Observation of Teaching and Learning | Planning and Work Scrutiny | Surveys (parents, pupils & staff) Audits of CPD needs – staff |
| Collaboration with other schools and across LA Boundaries | CPD Strategy/Plan | CPD evaluation records | In house and external Moderation |
| SIAMS Report |  |  |  |

| Staffing Responsibilities and Class Organisation |  |  |  |
| --- | --- | --- | --- |
| Claire Warner – Headteacher RE, Collective Worship, Geography, Computing |  |  |  |
| Class | Name | Role | Subject Leader/Responsibility |
| CHERRY CLASS Reception | Lauren Power | Class teacher | EYFS and Physical Education (PE) |
|  | Nicola White | Teaching assistant | Attendance |
| WILLOW CLASS Year 1/2 | Lorna Draper | Class teacher | Special Needs and Disabilities (SENDCo), Music and Personal, Social & Health Education (PSHE) |
|  | Caroline Jackson | Teaching Assistant | First Aid Lead/ Mental Health First Aider |
| Beech CLASS Year 3/4 | Joanne Bennett | Deputy Headteacher (D H) Class Teacher 0.8 | English, Art, Science and Personal, Social & Health Education (PSHE) |
|  | June Gibson | Teaching assistant | Speech and Language Support |
| OAK CLASS Year 5/6 | Lynsey Eley | Class Teacher 0.8 | Deputy Designated Lead for Safeguarding, Mathematics, History, Modern Foreign Languages (MFL) and Educational Visits (EVC) |
|  | Catherine Griffin-Jones | Class Teacher 0.2 | Design & Technology 0.1 in Beech Class covering D H 0.1 in Willow Class covering SENDCo |
|  | Melissa Harris | Teaching assistant | WELLCOM Champion/ Speech and Language support |